## Checklist
Phase | Step | Task | Owner | Output | When | Status | Due date | Notes | Page section
Scope | 1 | Choose Type 1 or Type 2 | Executive sponsor | Report type and target date | Start |  |  |  | https://soc2auditors.org/insights/soc-2-compliance-checklist/#step-1-choose-type-1-or-type-2
Scope | 2 | Select the Trust Services Criteria | Security lead, with sales | Criteria in scope | Start |  |  |  | https://soc2auditors.org/insights/soc-2-compliance-checklist/#step-2-select-your-trust-services-criteria
Scope | 3 | Define the boundary and system description | Engineering lead; legal and executive sign-off | Signed boundary, draft description | Before building controls |  |  |  | https://soc2auditors.org/insights/soc-2-compliance-checklist/#step-3-define-the-system-boundary-and-draft-the-system-description
Build |  | Build the ten control areas | One owner per control | Policies, configurations, first review records | Before the window opens (Type 1: before fieldwork) |  |  |  | https://soc2auditors.org/insights/soc-2-compliance-checklist/#phase-2-build-controls
Readiness | 4 | Run a gap assessment | Security or compliance lead | Gap register | Before the window opens (Type 1: before fieldwork) |  |  |  | https://soc2auditors.org/insights/soc-2-compliance-checklist/#step-4-run-a-gap-assessment-against-your-chosen-tscs
Readiness | 5 | Build the evidence repository | Audit coordinator | Evidence folders by control | Before the window opens (Type 1: before fieldwork) |  |  |  | https://soc2auditors.org/insights/soc-2-compliance-checklist/#step-5-build-your-evidence-repository
Readiness | 6 | Assign owners and run a mock audit | Security lead | Owner register; findings fixed | Before the window opens (Type 1: before fieldwork) |  |  |  | https://soc2auditors.org/insights/soc-2-compliance-checklist/#step-6-assign-control-ownership-and-run-a-mock-audit
Audit | 7 | Engage the auditor | Executive sponsor or legal | Engagement letter with the period dates | Type 2: before the window opens. Type 1: 4–6 weeks before fieldwork |  |  |  | https://soc2auditors.org/insights/soc-2-compliance-checklist/#step-7-select-and-engage-your-auditor
Audit |  | Run controls and close evidence monthly | Control owners, audit coordinator | Monthly evidence manifest | 3 to 12 months (Type 2 only) |  |  |  | https://soc2auditors.org/insights/soc-2-compliance-checklist/#monthly-evidence-close-during-a-type-2-window
Audit | 8 | Prepare for fieldwork | Audit coordinator | PBC tracker with evidence staged | Before fieldwork |  |  |  | https://soc2auditors.org/insights/soc-2-compliance-checklist/#step-8-prepare-for-fieldwork
Audit | 9 | Support fieldwork | Audit coordinator | Closed request log | Fieldwork, a few weeks |  |  |  | https://soc2auditors.org/insights/soc-2-compliance-checklist/#step-9-support-fieldwork
Audit | 10 | Review the draft and prepare bridge letters | Executive sponsor, audit coordinator | Management response; final report | After fieldwork |  |  |  | https://soc2auditors.org/insights/soc-2-compliance-checklist/#step-10-review-draft-report-and-issue-bridge-letters-if-needed
Audit | 11 | Set up annual renewal | Security lead | Next period's control calendar | The day the window ends |  |  |  | https://soc2auditors.org/insights/soc-2-compliance-checklist/#step-11-set-up-annual-renewal

## Control areas
Control area | Est. build time | Evidence auditors request | Common finding | Owner | Status | Notes | Guide
Access control | 3–6 weeks | Quarterly access review records with manager sign-off MFA enforcement screenshots Provisioning and termination workflow logs | Undocumented reviews or active accounts for terminated employees |  |  |  | https://soc2auditors.org/insights/soc-2-access-control-policy-template/
Data encryption | 2–4 weeks | Encryption standard policy (approved, versioned) KMS configuration screenshots Key rotation audit log | Keys co-located with the data they protect; rotation schedule in policy but not followed in practice
Security policies | 4–8 weeks | Policy documents with version history Executive approval evidence Employee acknowledgment log (name, date, policy) | Policy exists but no executive approval or acknowledgment log
Logging and monitoring | 3–5 weeks | SIEM configuration screenshots Log retention evidence covering the observation window Review sign-off records | Log retention gaps or no evidence of periodic review by a named reviewer |  |  |  | https://soc2auditors.org/insights/soc-2-security-controls/
Change management | 2–4 weeks | Change tickets with request, peer review, test result, and deployment record CI/CD pipeline configuration | Emergency changes approved after the fact; no separation of duties on approvals |  |  |  | https://soc2auditors.org/insights/soc-2-change-management-controls/
Incident response | 3–6 weeks | Tabletop exercise records (dated, named participants, findings) Post-incident reviews for any incidents in the period | Plan exists on paper but no tabletop exercise record
Vulnerability management | 3–5 weeks | Authenticated scan reports (monthly) Remediation tracking tickets Risk-acceptance records for approved delays | Critical findings aged past the policy's own SLA with no risk-acceptance sign-off
Vendor risk | 4–8 weeks | Vendor inventory with risk classification SOC 2 Type 2 reports or ISO 27001 certificates from critical vendors Contracts with security and breach notification clauses | Vendors onboarded without assessment; no security clauses in contracts
Employee training | 2–3 weeks | Training completion log (name, date, course) Phishing simulation results, if you run them | Completion records not tracked or missing for new hires |  |  |  | https://soc2auditors.org/insights/soc-2-security-controls/
Business continuity | 6–12 weeks | RTO and RPO for each critical system Backup configuration evidence Recovery test results with the gaps found and how they were fixed | Recovery plan never tested; no RTO or RPO validated by a real test |  |  |  | https://soc2auditors.org/insights/soc-2-business-continuity-controls/